## Slide 1
SWI / C08 PROJECT STATUS / HOSPODA DEVS
01
EXECUTIVE PROJECT STATUS
What is the current delivery position, what threatens it, and what decision is needed?
PROJECT / TEAM: Hospoda Devs (Petera, Kovařčík, Křižák)
REPORTING BASELINE: c07-reporting-baseline
REPORT DATE / OWNER: 29. 10. 2026 / Michal Křižák
SWI C08 | Reporting baseline: c07-reporting-baseline | Project: Hospoda Devs | Report date: 29. 10. 2026
PROJECT / TEAM
Rezervace stolů v hospodě / Hospoda Devs
OVERALL DELIVERY STATUS
AMBER / AT RISK
Ověřeno 142/142; chybí review C07 a zástupnost (R-01).
MOST IMPORTANT DELIVERED EVIDENCE
BR-02 drží při souběhu: lock-mechanism test + 10× zátěž, 0 porušení (c07-postgres-verification.json).
TOP DELIVERY CONSTRAINT
Znalosti u 1 člena (28/46 commitů) → riziko slabé obhajoby CP1 (R-01 HIGH).
EXECUTIVE ASSESSMENT
CP1 obhajitelné, pokud do 30. 10. projde review + merge c07 a do 1. 11. generálka.
DECISION / SUPPORT REQUIRED
Schválit dispozice F1/F2 a práh p95 ≤ 500 ms / tým / 30. 10. 2026

## Slide 2
SWI / C08 PROJECT STATUS / HOSPODA DEVS
02
SCOPE & DELIVERY EVIDENCE
Enter YES / PARTLY / NO (or justified N/A). A feature is VERIFIED only with relevant executed evidence.
PROJECT / TEAM: Hospoda Devs (Petera, Kovařčík, Křižák)
REPORTING BASELINE: c07-reporting-baseline
REPORT DATE / OWNER: 29. 10. 2026 / Michal Křižák
SWI C08 | Reporting baseline: c07-reporting-baseline | Project: Hospoda Devs | Report date: 29. 10. 2026
Capability / baseline item
Specified
Designed
Implemented
Verified
Evidence link / remaining gap
Create reservation
YES
YES
YES
YES
REQ-01 OP-01; V-01.1–7 (F2 opraveno 29. 10.)
Check availability
YES
YES
YES
YES
REQ-02 OP-02; AvailabilityService; V-02.1–7
Confirm / approval
YES
YES
YES
YES
REQ-03/04/06; ADR-03, C05 DD; DD-T1–T11, V-04R.1–8
Cancel reservation
YES
PARTLY
YES
YES
REQ-05 OP-04; V-04.3, V-04R.3/.5; gap: mimo C05 DD
Business rule / invariant
YES
YES
YES
YES
BR-02; ADR-03; lock-mechanism; gap: ruční SQL (R-02)
Quality scenario (C04)
YES
YES
YES
PARTLY
Q 10×: p95 hot 145–239 ms ≤ 500; jen lokálně, 1 proces
IMPORTANT EVIDENCE GAP
Kvalita 10× je ověřena jen lokálně v jednom procesu (není SLA); běh na prezentačním stroji zatím neověřen (R-03).

## Slide 3
SWI / C08 PROJECT STATUS / HOSPODA DEVS
03
SCHEDULE, RESOURCES & DEPENDENCIES
Use real owners and credible plan-versus-forecast dates. Report missing plans as a gap; do not invent progress.
PROJECT / TEAM: Hospoda Devs (Petera, Kovařčík, Křižák)
REPORTING BASELINE: c07-reporting-baseline
REPORT DATE / OWNER: 29. 10. 2026 / Michal Křižák
SWI C08 | Reporting baseline: c07-reporting-baseline | Project: Hospoda Devs | Report date: 29. 10. 2026
Work package / milestone
Owner
Committed plan
Actual / forecast
Health and evidence
Uzavřít nálezy C06 (F1, F2)
Michal
2. 11. 2026
29. 10. 2026
GREEN: opraveno, 142/142
Lidské review C07 + merge PR c07
Jarda
30. 10. 2026
ETA 30. 10.
AMBER: review zatím nezapsáno
Čistý běh na prezentačním stroji
Honza
1. 11. 2026
ETA 1. 11.
AMBER: 3 platformy OK, tento stroj ne
Plán CP2
Jarda
chybí
plán do 5. 11.
AMBER: mezera v plánování
TEAM CAPACITY / SINGLE POINT OF FAILURE
Jarda: 28/46 commitů, PostgreSQL setup. Záloha: generálka A, každý přednese cizí část (R-01).
EXTERNAL / CRITICAL DEPENDENCY
embedded-postgres 16.14 beta + síť pro npm ci; záloha docker compose (Honza).

## Slide 4
SWI / C08 PROJECT STATUS / HOSPODA DEVS
04
TOP RISKS, TREATMENT & RESIDUAL
Use up to three risks from section B. A planned control does not lower the ACTUAL residual risk.
PROJECT / TEAM: Hospoda Devs (Petera, Kovařčík, Křižák)
REPORTING BASELINE: c07-reporting-baseline
REPORT DATE / OWNER: 29. 10. 2026 / Michal Křižák
SWI C08 | Reporting baseline: c07-reporting-baseline | Project: Hospoda Devs | Report date: 29. 10. 2026
Risk / source
Initial L/I + priority
Response strategy
Treatment, owner & evidence
Expected / actual residual
Trigger / acceptance
R-01 People: znalosti u 1 člena → nikdo jiný neobhájí → ztráta bodů CP1
L2 / I3
HIGH (6)
MITIGATE
Generálka, cizí části / Michal
1. 11.; neprovedeno
Expected: L1/I3 MEDIUM
Actual: NOT VERIFIED
Otázka bez odpovědi
tým
R-02 Technical: zápis mimo Lifecycle (import, SQL) → 2 CONFIRMED → porušení BR-02
L1 / I3
MEDIUM (3)
MITIGATE
Import kontroluje BR-02 / Jarda
29. 10.; ověřeno testem
Expected: L1/I3 MEDIUM
Actual: L1/I3 MEDIUM (SQL zůstává)
Nový zápis mimo LC
Jarda
R-03 Release: npm ci / embedded PG selže na prezentačním PC → ukázka padne
L2 / I2
MEDIUM (4)
MITIGATE
Běh den předem + JSON záloha / Honza
1. 11.; neprovedeno
Expected: L1/I2 LOW
Actual: NOT VERIFIED
npm ci / start selže
Honza
OPEN ISSUES (NOT RISKS)
I-01: npm test přepisuje sledované c03-*.json → riziko commitu změněné evidence; Jarda; oddělit výstupy do CP2. I-02: bod 10 C02 čeká na vyučujícího.
Risk ranking: L x I (1-2 LOW; 3-4 MEDIUM; 6-9 HIGH). Actual residual = NOT VERIFIED until treatment effectiveness is evidenced.

## Slide 5
SWI / C08 PROJECT STATUS / HOSPODA DEVS
05
NEXT ACTION PLAN
Prioritise four actions. Each must have one owner, a date and an observable Definition of Done.
PROJECT / TEAM: Hospoda Devs (Petera, Kovařčík, Křižák)
REPORTING BASELINE: c07-reporting-baseline
REPORT DATE / OWNER: 29. 10. 2026 / Michal Křižák
SWI C08 | Reporting baseline: c07-reporting-baseline | Project: Hospoda Devs | Report date: 29. 10. 2026
Priority / action
Owner
Due date
Definition of Done / evidence
Finding / risk link
P1 Review C07 + merge PR c07
Jarda
30. 10. 2026
Review zapsáno; tag c07-reporting-baseline na main
F1, F2
P2 Generálka obhajoby A
Michal
1. 11. 2026
Každý zodpoví otázky k cizí části
R-01
P3 Čistý běh na prezentačním PC
Honza
1. 11. 2026
npm ci + npm test 142/142, log
R-03
P4 Plán CP2 + oddělit výstupy testů
Jarda
5. 11. 2026
Plán s vlastníky v repu; I-01 uzavřeno
R-04, I-01
IF THE PLAN FAILS
Neprokáže-li generálka zástupnost do 1. 11.: obhajobu A přednese autor každé části a R-01 zůstává HIGH; rozhodne tým 1. 11.

## Slide 6
SWI / C08 PROJECT STATUS / HOSPODA DEVS
06
MANAGEMENT CONCLUSION & DECISION
The conclusion must agree with the reporting baseline, tested evidence, risk register and action plan.
PROJECT / TEAM: Hospoda Devs (Petera, Kovařčík, Křižák)
REPORTING BASELINE: c07-reporting-baseline
REPORT DATE / OWNER: 29. 10. 2026 / Michal Křižák
SWI C08 | Reporting baseline: c07-reporting-baseline | Project: Hospoda Devs | Report date: 29. 10. 2026
DEMONSTRABLY COMPLETE
C01–C05 uzavřeno (tagy c03-architecture, c05-detailed-design); F1/F2 opraveny, 142/142 na PostgreSQL 16.14; BR-02 pod 10×: 0 porušení, p95 ≤ 239 ms.
OPEN / NOT VERIFIED
Lidské review C07, merge c07, běh na prezentačním PC, plán CP2, I-01 (přepisování evidence).
TOP RISK / RESPONSE / ACTUAL RESIDUAL
R-01; Michal; generálka cizích částí; actual NOT VERIFIED
REQUESTED DECISION / OWNER / DUE
Schválit dispozice F1/F2 a práh 500 ms / tým / 30. 10. 2026
OVERALL STATUS & DELIVERY FORECAST
AMBER - CP1 dosažitelné: kód a důkazy hotové (142/142, zátěž); zbývá review, merge a zástupnost týmu (R-01).